Project Management Concepts

- Project vs. Operations

  - Projects = a new venture that does not yet exist

  - Operations = repeatable steps

  - Two different skill sets

- Phases of Project

  - Business Planning / Dreaming

  - Warming Up the Project

  - HOT Project = ACTION

  - Wrap Up and follow through = Closing the Project

- Communication

  - The primary responsibility of the project manager – hire for this ability

  - Over communication is ideal

  - Most problems in the project will come as the result of miscommunication or the details not being as clear as you’re assuming they are

    - Keeping “Assumptions” as a part of the conversation and discussing openly what you’re assuming helps minimize miscommunications.

    - Recommend Video: Why Can’t I Speak the Way I Do in My Mind

  - Social Media: key for communicating with your most important Stakeholder: the community

  - Document Sharing Solution – Google Drive, Sharepoint, etc.

- Project Scope

  - Idea Wall Tool & Technique

  - “Scope Creep”

  - “Mission Critical” or “After Opening”

  - Continually reassess as you get closer to opening

- Rolling Wave Planning

  - Progressive Elaboration

  - Plan in detail the current phase, the next 1-4 weeks

  - Plan loosely areas of the project that are further away than that

  - As you make progress, plan the next upcoming section in more detail

- Requirements vs. Tasks  –

  - Template: Mod1_5 Task Tracking & Scheduling Dependencies

  - “Begin with the End in Mind” – Figure out the end and work your way backwards to create the list of what needs done

  - Get specific about the vision –“Bakery” gets broken down into: fresh-baked cinnamon rolls, breads, cookies, scones, custom cake orders, cupcakes, thaw and sell items, and other custom party trays.

  - Other terms to know

    - Constraints

      - We don’t intend to upgrade the electrical so the oven will have to be below #### power threshold

    - Dependencies

      - Example: the floor can’t be stained and finished until the plumber is done cutting into the floor to lay the plumbing for the refrigeration units

    - Traceability

      - Who requested each individual requirement - if you run into time / budget issues - this is your point of contact to follow back up with for more information, to delay or eliminate the item from the project scope.

  - Requirements vs. Tasks

    - Requirement: Purchase oven for bakery

    - Tasks:

      - Discuss oven specs with grocery warehouse or other trusted source – get recommendations for both new and used equipment

      - Research used ovens

      - Get quotes on new ovens

      - Consult with electrician on electrical updates that may be needed

      - Compare used options with new quotes and decide which to purchase

      - Once decided, provide oven specs to electrician to confirm/finalize electrical updates that may be needed

      - Receive oven in store and schedule with proper contractor for installation

      - Once installed, confirm the oven is working for its intended purpose

      - Make sure appropriate personnel is trained in how to use the oven

  - Task List

    - Use ID numbers on tasks to track details, due dates, team members assigned, priority level, etc.

- Budget Management

  - Budget for Time = Timeline / Dependencies

  - Budget for Money

    - Quotes, quotes, quotes is how you build your budget and make sure it all fits together

      - Quotes give you estimates for time,  money, and dependencies

        - Example: if a contractor is the cheapest, but can’t fit you in until next year, you may need to select a more expensive quote to fit your timeline requirements

      - From the quotes you can build the “Budget” and “Schedule”

- Stakeholders –

  - Template: Mod1_4 Stakeholder Tracking

    - Name, Phone, Email

    - Types of Stakeholders

      - Project Team

        - Contractors

        - Employees

      - Community Members

      - Abstract SH like “the community”

        - Begin the relationship with the community ASAP/as soon as you’re “Ready”

          - “Readiness” – the clock on the financing is ticking and this is THE MOST IMPORTANT relationship your store has, knowing how to say “I don’t know yet” will speed up your readiness.

    - Project Role

    - Priority/Importance

- Professional & Advisory Support

  - Banker

  - Insurance Agents

  - Consultants

  - Board of Directors

  - Attorney

  - Accountant

  - Business / Personal Mentors