## Sheet1
Project Task Tracking & Scheduling Dependencies
Item ID # | Item Name | Status | Mission Critical | Project Area | Additional Areas | Dependent on Task # | Project Team Contact | Elaborated Description and Project Notes
1 | Examples | Examples | Yes / No | Examples | If a task belongs to more than one area, assign column e as main area and here you can list all other impacted areas | Example: you can't have the floor guys come until the plumber is done cutting into the floor to lay the plumbing for the refrigeration units. The floor task is dependent on the plumber's task | Who is responsible for making sure the details of this task are completed? | Highly recommend leaving a dated notes log in this column, for example: Dec 1, 2022: Left message for plumber to call me back Dec 3, 2022: Spoke with plumber and he's coming next week on Dec 10th - changed task status to Scheduled Dec 11, 2022: Plumber completed hanging the sink - changing task status to closed.
2 | Get quote from at least 2 refrigeration contractors | Complete |  | Building remodel
3 | Draft Project Charter | Not Started |  | Equipment
4 | Meet with at least 2 banks to discuss project funding | Pending Dependent Task |  | Human Resources
5 | Get POS recommendations from our grocery warehouse | Scheduled
6 |  | In progress
7
8
9
10
11
12
13
14
15
16
17
18
19